## COMPLETED SCHEMES
COMPLETED BABERGH LCWIP SCHEMES
CYCLING, WALKING OR BOTH | REFERENCE | SECTION/LOCATION FOR INTERVENTION | DESCRIPTION | TYPE OF PROJECT/DELIVERY PARTNER | COST | PROGRESS | STATUS | NOTES | SHORT, MEDIUM OR LONG TERM LCWIP ASPIRATION
Walking | Wenham Boardwalk upgrade | Section of boardwalk on PRoW at Wenham | Upgrading and extending boardwalk in key amenity area of parish, to extend the use of the route for a larger part of the year and to additional legal users. | Rights of Way | 3810 | 100% | Scheme delivered | Funded via distrcit council Rural England Prosperity Funding | Short
Walking | Freston/Holbrook boardwalk upgrade | PRoW between Freston and Holbrook | Re-laying of boardwalk and bridge, and widening it to 1.2m wide and installing grip strips plus new steps to access boardwalk | Rights of Way | 15135 | 100% | Scheme delivered | Funded via distrcit council Rural England Prosperity Funding | Short
Walking and cycling | Shimpling Bridlegate upgrade | PRoW (bridleway) at Shimpling | Upgrade of a bridleway gate that was unsuitable for legal users and meant those on horseback and with limited mobility could not use the structure. Now all legal users can easily use the structure and have access to the route. | Rights of Way | 1500 | 100% | Scheme delivered | Funded via distrcit council Rural England Prosperity Funding | Short
Walking | Great Cornard to Henny Swan Footpath | Public Right of way/Footpath alongside River Stour | Small bridge upgrade and re-surfacing scheme to upgrade the tourist route from Great and Little Cornard to the River Stour and commercial sites. Now usable for those with limited mobility, for example. | Rights of Way | 10000 | 100% | Scheme delivered | Funded via distrcit council Rural England Prosperity Funding | Short
Walking | Monks Eleigh: The Causeway | Monks Eleigh Footpath no. 12 | Resurfacing and floodproofing of key linkage between North and South parts of village. | Rights of Way (delivered by Parish Council) | 15424.5 | 100% | Scheme delivered | Funded via distrcit council Rural England Prosperity Funding, delivered by Parish Council | Short
Walking | Wherstead: New boardwalk | Wherstead Footpath no. 001 | Building of boardwalk over a floodplain area to ensure accessbility all year round. | Rights of Way | 4950 | 100% | Scheme delivered | Funded via distrcit council Rural England Prosperity Funding. | Short
Walking | Acton: Bun Meadow | Bun Meadow PRoW - between Clay Hall Lane and High Street Acton | Resurfacing in order to be brought up to standard and passable all year round | Rights of Way | 9600 | 100% | Scheme delivered | Funded via distrcit council CIL funding award | Short
Walking and cycling | PRoW improvements at Flatford/Stour Valley National Landscape | Stour Valley project area: delivering PRoW improvement works identified in partnership with the National Landscapes team – accessibility improvements to key honeypot. Covering a range of projects to allow walking in the National Landscape for a greater proportion of the year and to a larger amount of legal users. | Improvements to accessibility and surfacing in the Dedham Vale National Landscape in collaboration with the local NL team | Rights of Way | 35000 | 100% | Scheme delivered | Funded via distrcit council Rural England Prosperity Funding. | Medium
Walking | Acton to Great Waldingfield | PRoW network between the three settlements of Acton, Great Waldingfield and Chilton | Desire for an off road route/PRoW provision between Great Waldingfield to Acton via the airfield, linking in Chilton if feasible | Rights of Way | Approx. £5,000 for legal designation work - maybe other costs for implentation/surfacing works? | 100% | Scheme delivered | Legal works for a deed of dedication taken forwards by SCC. | Short

## Short Term
SHORT TERM BABERGH LCWIP SCHMES
CYCLING, WALKING OR BOTH | REFERENCE | SECTION/LOCATION FOR INTERVENTION | DESCRIPTION | TYPE OF PROJECT/DELIVERY PARTNER | INITIAL INDICITIVE/ESTIMATED COST | PROGRESS | STATUS | NOTES | PCT Score if available (officer use only - to determine column in G) | Potential to increase walking and cycling trips (if no data fromPCT, strava heatmap is used) | Population who would directly benefit from the intervention | Improvement in road safety | Delivery against policy objectives: BMSDC strategies and Neighbourhood Plan | Performance against Suffolk Local Transport plan | Importance of the intervention for particular user groups | Value for Money | Potential to be funded | Scheme feasability | Liklihood to enable/improve the feasability of other schemes | Dependency on other scheme | Local acceptability | Local desire | TOTAL SCORE /39 | SHORT, MEDIUM OR LONG TERM ASPIRATION | NOTE: To see the prioritisation scoring method please unhide columns M-Z.
Cycling | Shotley North Route, Section 5 | Between Freston and Ipswich | Segregated or off road cycle path alongside Freston Hill | Transport Strategy | £1,200,000 (On SCC list, this is estimated at £2,760,000, but this a longer stretch, not broken down into the same geographical stretches as distrcit LCWIP) | 20% | Initial concept started | Site visits and development work have been undertaken, but SCC Highways are struggling to design feasable intervention within contraints and guidance/standards. | 2 | 2 | 3 | 3 | 3 | 2 | 3 | 2 | 2 | 1 | 3 | 3 | 2 | 3 | 32 | Short
Walking & Cycling | Sproughton Underpass | A14 Underpass just south of Sproughton - near Church Lane | Improve access to, and quality of, underpass. Better lighting, improved surface and segreagation. | Transport Strategy | 12000 |  | Community con. |  | 1.61 | 1 | 3 | 1 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 3 | 3 | 2 | 31 | Short
Walking & Cycling | Sudbury to Great Cornard: off road route | Footpaths from The Gainsborough Trail/Meadow Walk (at Kingfisher Leisure Centre) across Friar's Meadow and alongside River Stour to Mill Tye at Great Cornard | Improve and smooth surface, remove barriers and drops/steps in level. | Rights of Way and/or Transport Strategy | 130000 | 40% | Initial concept started | SCC Highways have ringfenced £125,000 of Active Travel Funding for this scheme, paired with the implentation of a crossing over Bures Road at end of route, and have carried out stakeholder consultation. Waiting for PRoW to cost up the footpath sections. | No data | 2 | 3 | 1 | 3 | 3 | 3 | 2 | 1 | 2 | 2 | 3 | 3 | 3 | 31 | Short
Walking & Cycling | Great Cornard: Bures Road | Bures Road | Desire for safe crossing point from Mill Tye area, plus interventions for safe off-road cycling and walking space,also access to river footpath without walking on roadside. | Rights of Way and/or Transport Strategy | 200000 | 20% | Initial concept started | SCC Highways have ringfencedsome Ative Travel Funding for the crossing point and investigated what else might be able to be delivered to improve active travel safety on the road - stakeholder consultation being carried out. Linked to scheme above. | 2 | 2 | 2 | 2 | 3 | 3 | 2 | 2 | 3 | 2 | 3 | 2 | 2 | 3 | 31 | Short
Walking | Monks Eleigh: Church Hill footway lighting | Pathway just off Church Hill, between Chirch and Recreation Ground/Village Hall | Install landscape appropriate lighting so that pedestrians can access/safely use path in evenings and throughout winter | Transport Strategy | 17900 | 80% | Delivery started | Funded via distrcit council Rural England Prosperity Funding, being delivered by Parish Council in partnership with SCC street lighting team. Electric supply has been installed - lighting units to follow. | No data | 1 | 2 | 3 | 3 | 1 | 3 | 2 | 3 | 3 | 1 | 3 | 3 | 3 | 31 | Short
Walking | Newton: Pedestrian Crossing across A134 | Proposed location is in the centre of the village, at the bus shelter adjacent to Rectory Road. | A signalised pedestrain crossing and footway leading to it, to provide active travel connectivity between southern and northern parts of village (for access to services and ammenities). | Transport Strategy | £35,000 (based on generic costings for zebra crossing) | 30% | Proposal design made | Parish Council have conducted a parish survey to understand residents requirements and preferences for the location of a pedestrian crossing. SCC Highways provided some design proposal work to accompany this survey. | 3 | 2 | 2 | 3 | 3 | 1 | 2 | 2 | 2 | 3 | 2 | 3 | 2 | 3 | 30 | Short
Cycling | Sudbury: Girling St | Girling St / North St | Desire for a cycle path on the North Side and for traffic free access to Sainsbury's. | Transport Strategy | £390,000 for Girling St to Belle Vue Rroundabout or £190,000 for North St to East St |  | Community con. |  | 2.5 | 2 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 3 | 2 | 2 | 30 | Short
Cycling | Shotley: North to South, Western Connection (Off road, via Bridleways) | Bridleway 45 nr Freston, through Cutlers Wood, and Bridleway 12 toward Holbrook. | Previous ambition for a segregated or off road cycle path alongside B1080 has proved unviable, so the suggestion to improve the off-road connectivity (put forwards by the Shotley Peninsula Cycling Campaign) has been taken forwards as an alternative. | Rights of Way | £7,275 for Birdleway 45, and £22,475 for Bridleway 12 | 80% | Funding secured | District CIL funding awarded to SCC PRoW team in March 2025 to deliver both bridelway improvement projects. | 1.75 | 1 | 2 | 1 | 3 | 1 | 2 | 3 | 3 | 3 | 2 | 3 | 3 | 2 | 29 | Short
Walking | Great Waldingfield: off road connections | PRoW network between Folly Road, The Street and The Heath/B115 | Desire for improvements to off-road active travel routes - resurfacing and improvements to Footpaths Number 11 and 12. | Rights of Way | 18450 | 80% | Funding secured | £17,450 of district council CIL funding agreed in March 2025. Works due to be undertaken November 2025. | 1.81 | 1 | 2 | 1 | 2 | 1 | 3 | 3 | 3 | 3 | 1 | 3 | 3 | 3 | 29 | Short
Walking | Ballingdon: Footpath No. 29 | PRoW FP no. 29, near Pinecroft Rise, Ballingdon | Footpath improvements / resurfacing | Rights of Way | 20275 | 80% | Funding secured | District CIL funding awarded to SCC PRoW in September 2024 to deliver this scheme - so must be delivered by October 2025. | No data | 2 | 1 | 1 | 2 | 1 | 2 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 29 | Short
Cycling | Sudbury: Borehamgate / Cornard Road | Cornard Road (North side) from Co-Op to roundabout | Desire for a cycle path on the North Side and for traffic free access to Sainsbury's. | Transport Strategy | 30000 |  | Community con. | Investigation needed into where the path should go. The existing cycle path runs on the south side, Toucan crossings have been put in place but there is very little footpath on the north side between the crossing and the supermarket. Maybe a better solution would be to add signage telling cyclists to dismount? | 2.1 | 2 | 2 | 3 | 3 | 3 | 2 | 3 | 2 | 1 | 2 | 2 | 2 | 2 | 29 | Short
Walking & Cycling | Hartest: Restrict Byway at The Green | PRoW restrcited Byway No. 13, near The Green, Hartest | Byway improvements / resurfacing to improve accessibility | Rights of Way | 25495 | 80% | Funding secured | District CIL funding awarded to SCC PRoW in September 2024 to deliver this scheme - project should be completed winter 2025/26 | No data | 2 | 2 | 1 | 2 | 1 | 1 | 3 | 3 | 3 | 1 | 3 | 3 | 3 | 28 | Short
Cycling | Assington Thicks | Footpath near Assington Thicks | Desire for off-road cyling route to be permitted /enabled to create a route to Sudbury | Rights of Way | £5,000 (assuming designation change only) | 5% | Community con. |  | No data | 2 | 1 | 1 | 3 | 1 | 2 | 3 | 3 | 3 | 1 | 3 | 3 | 2 | 28 | Short
Cycling, Walking or both | Cattawade A137 | A137 | Desire for 2 x dropped curbs to enable cycle route connectivity, general safety improvements to existing shared footway/cycleway, or an alternative offroad route via reclasification of footpaths | Transport Strategy | £6,000 for two dropped kerbs | 5% | Community con. | Discussed with SCC Highways - possibility that this could be delivered via S106 relating to nearby development. | No Data | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 3 | 3 | 1 | 3 | 3 | 2 | 28 | Short
Cycling | Boxford: Cycle Parking provision | Boxford Villiage Centre | Desire for cycle parking to enable cycling into village for services and facilities | Transport Strategy | £1,000-£2,000 depending on style and amount | 10% | Talks- potential partners |  | 1.6 (based on Broad Steet/Ellis Street area) | 2 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | 3 | 1 | 3 | 3 | 2 | 27 | Short
Walking | Holbrook: Boardwalk off Fishponds Lane | The boardwalk section of Footpath 23, running Northwards from Fishponds Lane | Upgrading boardwalk to improve accessibility and safety, improving off-road connectivity between south and North/middle of village | Rights of Way | 4000 | 50% | Seek funding proposal | A funding appliaction for District CIL monies (£3,745.00) has been submitted by the PRoW team - due to be considered by cabinet in September 2025. | No data | 1 | 1 | 1 | 2 | 1 | 1 | 3 | 3 | 3 | 2 | 3 | 3 | 2 | 26 | Short
Cycling | Sudbury: town centre, access from South | East St / Market Hill / North St | Desire for continuous, joined up cycle routes connecting the town with surrounding residential areas. | Transport Strategy | £400,000 based on ~650m MH to King St, East St to Girling Rd & Nth St to Gainsborough Rd | 0% | Community con. |  | 1.8-3.0 | 2 | 3 | 2 | 3 | 3 | 2 | 2 | 2 | 1 | 2 | 1 | 1 | 2 | 26 | Short
Walking | Sudbury: town centre, access from East | Gainsborough Str / Friars St / Market Hill | Improved pedestrian crossing at access points to Market Hill | Transport Strategy | £130,000 based on 2x zebra crossings | 0% | Community con. |  | 2.81 | 2 | 1 | 1 | 3 | 3 | 1 | 2 | 3 | 2 | 1 | 3 | 3 | 1 | 26 | Short
Walking | Sudbury: Station Approach | Station approach, carpark | Improve pavements, particularly for prams / buggies | Transport Strategy | 675000 |  | Community con. |  | No data | 1 | 1 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 2 | 3 | 2 | 1 | 26 | Short
Cycling | Long Melford: Swanfield | Pedestrian cut through between Swanfield and Roman Way | Desire to widen/open up this pavement/path to allow cycling | Rights of Way and/or Transport Strategy | 18000 |  | Community con. |  | No data | 2 | 2 | 1 | 2 | 1 | 3 | 2 | 2 | 3 | 1 | 3 | 3 | 1 | 26 | Short
Walking & Cycling | Sudbury: Belle Vue | Access to park / improved junction | Desire for safe access to the park / improved junction. | Transport Strategy | £180,500 assuming pedestrian crossing, less if zebra. | 5% | Talks- potential partners |  | 2.1 | 2 | 2 | 1 | 3 | 3 | 2 | 2 | 1 | 1 | 3 | 1 | 2 | 2 | 25 | Short
Walking & Cycling | Long Melford: Borley Road | Where the Valley walk meets Borley Road | Improve the road crossing, potentially upgrade ongoing footpath to enable cycling. Create better route from end of Valley path onwards into viallage. | Rights of Way and/or Transport Strategy | £180,500 (crossing only - other connectivity to be considered as sperate scheme?) |  | Community con. | Sections of the route are located within the Essex border, so cross-boundary working/funding would be required. | 3.5 | 2 | 1 | 2 | 2 | 1 | 1 | 2 | 1 | 2 | 3 | 3 | 2 | 3 | 25 | Short
Cycling | Sudbury, Hamilton Road | Bus station / Hamilton Road / Great Eastern Road | Desire for more space / better segregation as part of Hamilton Road design. | Transport Strategy | £100,000 (based on existing road layout) | 5% | Initial concept started |  | 1.83 | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 22 | Short
Cycling | Bures: PRoW | Footpaths near Clicket Hill and Cuckoo Hill | Desire to open up path/upgrade to cycle route or bridleway to improve local cycle connectivity | Rights of Way | £12,000 for 2 x redesignations plus signage |  | Community con. |  | No data | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 3 | 3 | 1 | 21 | Short
Note on I4: Katherine Davies: Price list: New cycleway/footway = £600 per metre Dropped kerb = £3,000 each New signage = £500 per sign New zebra crossing = £65,000 New traffic signals = £200,000 Pedestrian/Cycle crossing single carriageway road = £180,500 Pedestrian/Cycle crossing dual carriageway road = £250,000 Designating a Quiet Lane = £4,500 Rights of way stuff: unsealed surface – like crushed and rolled stone – is £35/m2. sealed surface, e.g. tarmac, is £80/m2. For any project that includes legal work (so changing the status from footpath to bridleway or diverting a route), the standard fee is £5,000. If buying land the minimum Environment Agency costs (£1,000), Planning Permission (£350) and Ecology Advice (£250). new fencing =£10/m new gates = £500 new footbridge £1000, new bridleway bridge = £3,000.
Note on M4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: using Geography: Middle Super Output Area, Cycling Flows: Route Network LSOA clickable and scenario: government target equality
Note on N4: Katherine Davies: 1 = if PCT is 0-2 2 = if PCT is 2 - 4 3 = if PCT is 4+
Note on U5: Katherine Davies: already on SCC radar for fuding.
Note on O6: Katherine Davies: getting people into Ipswich
Note on R6: Katherine Davies: this cycle route promoted on the Ipswich map, only just outisde the '15 minute walk' zone
Note on W7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Could negate the need for the more extensive work on Kings Hill.
Note on I8: Katherine Davies: to extend double the distance of the other Great Cornard to Sudbury scheme suggestion, the other side of Stannard Way
Note on X11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Could be linked to other Nth St schemes
Note on X15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Link with other works, belle vue roundabout.
Note on U21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: considering wider projects around sudbry (eg MH, bus station)
Note on U22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Wider MH works
Note on W23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Would link with cornard river path
Note on Q24: Katherine Davies: although this route is not specifically mentioned, the NDP referecnes cycle connectivity and safety in sections 3.21, 5.9, and anything to do with new development.
Note on S24: Katherine Davies: Travel to school
Note on X25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: potential link to Kings Hill / Cornard Road improvements
Note on F26: Katherine Davies: is this just outside of the district boundary?
Note on X27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hamilton Road quarter plans

## Medium Term
MEDIUM TERM BABERGH LCWIP SCHEMES
CYCLING, WALKING OR BOTH | REFERENCE | SECTION/LOCATION/ INTERVENTION | DESCRIPTION | TYPE OF PROJECT/DELIVERY PARTNER: | INITIAL INDICATIVE/ESTIMATED COST | PROGRESS | STATUS | NOTES | PCT Score if available (officer use only - to determine column in G) | Potential to increase walking and cycling trips (if no data fromPCT, strava heatmap is used) | Population who would directly benefit from the intervention | Improvement in road safety | Delivery against policy objectives: BMSDC strategies and Neighbourhood Plan | Performance against Suffolk Local Transport plan | Importance of the intervention for particular user groups | Value for Money | Potential to be funded | Scheme feasability | Liklihood to enable/improve the feasability of other schemes | Dependency on other scheme | Local acceptability | Local desire | TOTAL SCORE /39 | SHORT, MEDIUM OR LONG TERM ASPIRATION | NOTE: To see the prioritisation scoring method please unhide columns M-Z.
Cycling | Capel St Mary to Copdock/Washbrook | Route alongside A12 and into settlements. | Introduce segregated walking and cycling paths, signalised crossings, traffic calming measures, and improved junctions. Several hundred houses are due to be developed in Capel, so some/all funding could be secured through S106 for the scheme. This scheme could link up with the Woolsey Grange development in Sproughton. | Transport Strategy | £1m - £3m | 40% | Proposal design made | Community Consultation undertaken: https://storymaps.arcgis.com/collections/c3f3a4ad5ddf454f82f2f89d5a4b1c43?item=5. SCC have allocated Active Travel Funding to the devleopment of this scheme - £46,967 in 2023, and a further £185,000 in 2025. | 2.2 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 2 | 1 | 3 | 3 | 3 | 3 | 32 | Medium
Walking | Stuston | Alongside/following route of Stuston Road | Desire for off road pedestrian access into Diss (alongside/parallel to the route of the B1077) - Parish Council have drawn up plans | Transport Strategy | 510000 | 10% | Talks- potential partners |  | 2.1 | 2 | 2 | 3 | 3 | 1 | 3 | 2 | 2 | 1 | 1 | 3 | 3 | 3 | 29 | Medium
Cycling | Sudbury: Melford Road | Melford Rd | Desire for new cycle paths / better pavements / better segregation | Transport Strategy | £1,062,000 from York road to A134 roundabout |  | Community con. |  | 2.58-3.39 (various sections of Melford Road) | 2 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 3 | 1 | 2 | 28 | Medium
Cycling | Sudbury: Waldringfield Road | Waldringfield Rd roundabout | Improve cycling provision / new paths in view of Chilton Woods development to link through to town cente and railway | Transport Strategy | £25,000 based on resurfacing both roundabouts. |  | Community con. |  | 1.87 | 1 | 3 | 1 | 3 | 3 | 3 | 2 | 3 | 2 | 1 | 2 | 3 | 1 | 28 | Medium
Walking & Cycling | Sudbury: Acton Lane | Acton Lane / Springlands Way | Desire for segregated cycle / foot path linking the two sections of Acton Lane / Chilton Fields and Sudbury. SCC list suggests alternative route to be investigated. | Transport Strategy | 200000 |  | Community con. |  | 2.43 & 4.25 | 2 | 2 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 3 | 2 | 1 | 27 | Medium
Walking & Cycling | Sudbury, Friars Street | Friars Street | Introduction of a 20mph speed limit | Transport Strategy | 125000 |  | Community con. |  | 2.09 | 2 | 2 | 1 | 3 | 3 | 1 | 2 | 1 | 3 | 1 | 3 | 3 | 1 | 26 | Medium
Walking & Cycling | Sproughton | Sproughton Road near Sproughton Millenium Green | Reconfigure exisiting cycle path (issues of swerving round signs under bridge, and provision stopping short), and extend cycle path into the village | Transport Strategy | 840000 |  | Community con. |  | 1.53 | 1 | 2 | 2 | 3 | 3 | 2 | 2 | 1 | 1 | 2 | 3 | 2 | 2 | 26 | Medium
Walking and Cycling | Sudbury -Kone Vale Path | Kone Vale Path | Desire for Kone Vale path to be upgraded so surface is passable by foot and bike in all weathers | Rights of Way or Public Realm | £24,000 (or £11,000 if unsealed surface) |  | Community con. | Looks to be in distrcit council ownership, so improvements may be able to be undertaken by BDC Public Realm team. | No data | 2 | 3 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 3 | 3 | 1 | 26 | Medium
Walking | Cockfield: School Access | Church Lane, Cockfield | Current pavement provisions are narrow and not continous along the route to the school, meaning that pedestrains have to cross the lane for access. | Transport Strategy | Up to £180,000 for crossing, up to £322,000 for additional pedestrain safety measures such as pavement widening & guard rails. |  | Talks- potential partners | Initial/early stage advice from SCC Highways is that it may not be feasible to implement improvements due to constraints/lack of space in and around highway boundary. | No Data | 1 | 1 | 2 | 2 | 1 | 3 | 2 | 2 | 2 | 3 | 3 | 3 | 1 | 26 | Medium
Cycling | Sudbury / Great Cornard | Kings Hill | Better space and segregation for cyclists. | Transport Strategy | £200,000 (Stannard Road to mini roundabout) |  | Community con. |  | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 25 | Medium
Cycling | Sudbury | Church Field Road | Desire for improved cycle path and junctions along road. | Transport Strategy | 675000 |  | Community con. |  | No data | 2 | 2 | 3 | 3 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 1 | 25 | Medium
Walking & Cycling | Stone Street to Boxford (Section 1) | Alongside the A1071 (south side) to the east of Stone Street Road, section leading to River Box Bridge, and access down to the riverside path underneath the bridge. | Improve pedestrian & cycle access to the riverside 'underpass' connection | Rights of Way and/or Transport Strategy | £3,500-£8,000 depending on surface type + £5,000 legal fees + £1,600 and land price if needing to purchase land (if vergeside space not sufficient). Total indicative cost approx £15,000 excluding land purchase. | 10% | LCWIP feedback | Site visit undertaken, PRoW team unable to determine land ownership of path underneath bridge. | 2.33 | 2 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 2 | 3 | 3 | 2 | 2 | 25 | Medium
Walking & Cycling | Sudbury, A131 / Bulmer Rd | A131 near Sandy Lane / Bulmer Rd Business Park | Desire for improved pavements / segregated cycle path | Transport Strategy | 60000 | 0% | Community con. |  | 3.75 | 2 | 3 | 1 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 24 | Medium
Walking & Cycling | Hadleigh: A1071 Crossings | A1071 Road Junction/crossing | Desire for safer pedestrain and cyclsits crossings at busy junctions | Transport Strategy | £37,000 for two crossings | 0% | Community con. |  | 1.67 | 1 | 2 | 3 | 1 | 1 | 2 | 2 | 1 | 2 | 2 | 3 | 2 | 2 | 24 | Medium
Walking | Sudbury | Station Road | Improved space for pedestrians on the east side of station road. | Transport Strategy | £12,000 based on resurfacing existing paths | 0% | Community con. |  | 1.83 | 1 | 1 | 1 | 3 | 3 | 2 | 2 | 1 | 2 | 1 | 3 | 3 | 1 | 24 | Medium
Walking | Hintlesham | Pond Hall Road, South West of Hintlesham | Desire for off road pedestrian space between Pond Hall Road and Duke Street in order to link up circular walking route and improve village access | Rights of Way | £42,000 (based on £35,000 for surface + legal / environmental fees.) | 0% | Community con. |  | 1.6 | 1 | 1 | 3 | 2 | 1 | 1 | 2 | 2 | 3 | 1 | 3 | 3 | 1 | 24 | Medium
Cycling | Sudbury: East Street | Acton Lane / East Street | Desire for a cycle path at East Street | Transport Strategy | £300,000 (based on Acton Lane to Market Hill stretch, £180,000 if stop at Girling St) |  | Community con. |  | 2.01 | 2 | 2 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 24 | Medium
Walking | Sudbury Gainsborough St | Near Christopher Lane | Desire to reduce the road to single lane and widen footpaths. | Transport Strategy | £48,000 if just the bit to MH additional 90k if includes the whole stretch to School St |  | Community con. |  | 2.8 | 2 | 2 | 1 | 3 | 3 | 2 | 2 | 1 | 2 | 1 | 3 | 1 | 1 | 24 | Medium
Cycling | The Long Melford Walk | The Melford Walk / Old Railway Line | Requests to upgrade this path to allow/enable cycling, and better connectivity at end of trail | Rights of Way and/or Transport Strategy | £225,000 (5k designation change, 1k signage, 180k for road crossing, 30k for RW unsealed surface) |  | Community con. |  | No data (off road) | 2 | 2 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 3 | 2 | 3 | 24 | Medium
Cycling | Hadleigh Town Centre | High Street /Cross Maltings | Desire for segragated cycle path down high street/through Hadleigh, and improved junction crossinsg for cyclsts and pedestrians | Transport Strategy | 420000 |  | Community con. |  | 1.61 | 1 | 3 | 2 | 3 | 1 | 2 | 2 | 1 | 1 | 2 | 3 | 1 | 2 | 24 | Medium
Cycling | Sudbury - Aubrey Drive | Aubrey Drive / Waldringfield Road Junction | Desire for current cycle path to be linked as it currently stops on the west side after the Waldingfield Road junction. | Transport Strategy | £65,000 - based on a new zebra crossing linking the two ends of the cycle path. |  | Community con. |  | 1.85 | 1 | 1 | 1 | 3 | 3 | 2 | 2 | 1 | 3 | 1 | 3 | 1 | 1 | 23 | Medium
Cycling | Sudbury, Kings Street | Kings Street | Should be 2-way for cyclists, improved crossings and better space. | Transport Strategy | £200,000 including legal |  | Community con. |  | 2.4 | 2 | 2 | 3 | 3 | 3 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 23 | Medium
Walking & Cycling | Long Melford: Bull Lane | Bull Lane | Better active travel link into Long Melford from/to Acton and Industrial Estate desired, currently no segregation from traffic. Feedback suggests sufficient room exists on at least one side of the road to put in at the minimum a shared path but ideally a pavement and segregated cycle path to LTN 1/20 standard. Would also need crossing over bypass | Transport Strategy | 1320000 |  | Community con. |  | 2.71 | 2 | 2 | 3 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 23 | Medium
Walking & Cycling | Sudbury: approach into Town centre from the North | Juctions of Melford Road / Gainsborough Road (near Beaconsfield Road) / Girling Street | Desire for improved junctions/crossings and better visibitily/safetly and provision for pedestrians and cyclists. | Transport Strategy | 225000 | 50% | Proposal design made | SCC Highways have previously ringfenced Active Travel/LTP Funding for this scheme and have submitted planning application/consultation. Further info: https://www.suffolk.gov.uk/roads-and-transport/transport-planning/improvements-for-walking-cycling-and-wheeling/melford-road-sudbury | 2.83 | 2 | 2 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 23 | Medium
Walking & Cycling | Stone Street to Boxford (Section 2) | Underneath the A1071 between Stone Street and Boxford, section of riverside walk | Improve the riverside 'underpass' connection - improvements to surface and access and either end. Widening is unlikely to be possible, but other intervention (signage, marking, cutting back vegetaion) could make this a more useable shared space path. | Rights of Way | £400 surface + £700 for guardrail. Maybe additional costs for lighting or gate replacement, but could potentially be delivered around £2,000 | 10% | LCWIP feedback | Site visit undertaken, PRoW team unable to determine land ownership of path underneath bridge. | 2.33 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 2 | 3 | 2 | 2 | 2 | 23 | Medium
Walking | Sudbury Great Eastern Road | Between Roys and Station / Waitrose | Improve the junctions / crossings by Roys. Mini roundabout at station / waitrose entrance | Transport Strategy | £260,000 based on 2x new zebra crossings and legals etc plus mini roundabout |  | Community con. |  | No data | 2 | 2 | 1 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 21 | Medium
Walking | Sudbury: Netwon Road | Newton Road | Desire for the missing footway on the south side to be replaced. | Transport Strategy | £200,000 based on Belle Vue Road to Ingrams Well Road |  | Community con. |  | 2 | 1 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 20 | Medium
Cycling | Cattawade Decoy Pond | Factory Lane | Desire for south side of the road from the Cattawade Crown to Decoy Pond be made shared use walking/cycling, and iprovement to surface at link up to bridleway | Rights of Way and/or Transport Strategy | £10,000 for cycle lane and redesignation |  | Community con. |  | No data | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 20 | Medium
Cycling | Sudbury: Market Hill | Market Hill | Suggestion to make north side eastbound to allow cyclists to cross town. IE change direction of traffic | Transport Strategy | £100,000 assuming contraflow cycle lane with std legal fee. |  | Community con. |  | 2.44 (G'boro St not MH) | 1 | 1 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 20 | Medium
Walking & Cycling | Sudbury: York Road | York Road | Desire for creation of safer walking and cycling provisions | Transport Strategy | £192,000 (could be cheaper if only changing designation of current footpath) |  | Community con. |  | No data | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 20 | Medium
Note on I4: Katherine Davies: Price list: New cycleway/footway = £600 per metre Dropped kerb = £3,000 each New signage = £500 per sign New zebra crossing = £65,000 New traffic signals = £200,000 Pedestrian/Cycle crossing single carriageway road = £180,500 Pedestrian/Cycle crossing dual carriageway road = £250,000 Designating a Quiet Lane = £4,500 Rights of way stuff: unsealed surface – like crushed and rolled stone – is £35/m2. sealed surface, e.g. tarmac, is £80/m2. For any project that includes legal work (so changing the status from footpath to bridleway or diverting a route), the standard fee is £5,000. If buying land the minimum Environment Agency costs (£1,000), Planning Permission (£350) and Ecology Advice (£250). new fencing =£10/m new gates = £500 new footbridge £1000, new bridleway bridge = £3,000.
Note on M4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: using Geography: Middle Super Output Area, Cycling Flows: Route Network LSOA clickable and scenario: government target equality
Note on N4: Katherine Davies: 1 = if PCT is 0-2 2 = if PCT is 2 - 4 3 = if PCT is 4+
Note on I5: Katherine Davies: estimated price on SCC list
Note on Z6: Katherine Davies: assuming Parish Council views are reflective of the community
Note on M9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scores for the North and South sections of Acton Lane respectively (@ 50% of network in PCT) At 90% we see potential for south side of springlands at 6.5 around Stanley Wood Ave. @ 30% Springlands between Acton Lane (N) and Stanley Wood Ave scores 2.29.
Note on Y9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on introducng a footpath connecting Stanley Wood Ave and Acton Lane. Currently culdesac backing onto a field.
Note on Q10: Katherine Davies: all Sudbury schemes score 3 for this criteria as local plan suports improved active travel links in Sudubry
Note on R10: Katherine Davies: all Sudbury schemes to score a 3 for this criteria as "The main focus of the plan is to reduce the need for travel by car"
Note on R11: Katherine Davies: if getting people into Ipswich
Note on M12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PCT @90% of network actually gave theresult 'infinite' based on dividing by zero (baseline figure). Used Strava :-)
Note on R14: Katherine Davies: Great Cornard within '15 minute cycle' ring in LTP
Note on I17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Difficult to quantify as they don't specify a route, just a junction Reply: Potentially full junction redesign. Reply: I've done an estimate based on a mini roundabout installation which is comparable with junction reconfiguration
Note on O23: Katherine Davies: Link into Sudbury for other villages
Note on Q23: More about designation of green spaces?
Note on S23: Katherine Davies: due to the link into Sudbury
Note on Y23: Katherine Davies: Concern about impact on nature/biodiversity designated space
Note on Z23: Katherine Davies: Worth noting 60 agreements to this - most popular suggestion of entire consultation
Note on U26: Sarah Cave: MH development
Note on X26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Market Hill development
Note on Q27: Katherine Davies: NDP recognises Bull Lane safety issues, although does not specifically mention it as a potential cycle route
Note on S27: Katherine Davies: industrial estate emplyment site
Note on X28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Melford Road cycle lane
Note on X30: Sarah Cave: Hamilton Road Qtr
Note on M31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @50% network
Note on T34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Unless cheaper option is available

## Long Term
LONG TERM BABERGH LCWIP SCHEMES
CYCLING WALKING OR BOTH | REFERENCE | SECTION/LOCATION/ INTERVENTION | DESCRIPTION | TYPE OF PROJECT/DELIVERY PARTNER: RIGHTS OF WAY OR TRANSPORT STRATEGY | ESTIMATED COST | PROGRESS | STATUS | NOTES | PCT Score if available (officer use only - to determine column in G) | Potential to increase walking and cycling trips (if no data fromPCT, strava heatmap is used) | Population who would directly benefit from the intervention | Improvement in road safety | Delivery against policy objectives: BMSDC strategies and Neighbourhood Plan | Performance against Suffolk Local Transport plan | Importance of the intervention for particular user groups | Value for Money | Potential to be funded | Scheme feasability | Liklihood to enable/improve the feasability of other schemes | Dependency on other scheme | Local acceptability | Local desire | TOTAL SCORE /39 | SHORT, MEDIUM OR LONG TERM ASPIRATION | NOTE: To see the prioritisation scoring method please unhide columns M-Z.
Cycling | Shotley North Route, Section 4 | Between Woolverston and Freston | Segregated or off road cycle path alongside B1458 | Transport Strategy | 960000 | 5% | Initial concept started |  | 2 | 2 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 3 | 2 | 2 | 3 | 30 | Long
Cycling | Shotley South Route, Section 2 | Between Holbrook and Stutton | Segregated or off road cycle path alongside B1080/Holbrook Road | Transport Strategy | 1980000 | 0% | Talks- potential partners |  | 3 | 2 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 3 | 2 | 2 | 3 | 30 | Long
Walking & Cycling | Newton | Stretch of the A134 through Newton to Sudbury, past Perrywoods | Desire for segragated walking/scycling space alongside busy road | Transport Strategy | £2,040,000 (shorter section could be cheaper but still valuable) | 0% | Community con. |  | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 2 | 2 | 2 | 3 | 30 | Long
Cycling | Shotley South Route, Section 1 | Between Harkstead and Holbrook | Segregated or off road cycle path alongside Harstead Rd/Holbrook Road | Transport Strategy | 1740000 | 0% | Talks- potential partners |  | No data |  | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 3 | 2 | 2 | 3 | 28 | Long
Walking & Cycling | Sudbury Cornard River Walk | Cornard River Walk | Desire for new foot/cycle path | Transport Strategy | £1,000,000 (based on approx equivalent distance along the road of 1.1miles) | 0% | Community con. |  | No data | 2 | 2 | 1 | 3 | 3 | 3 | 2 | 1 | 2 | 1 | 3 | 3 | 2 | 28 | Long
Cycling | Shotley North Route, Section 2 | Between Shotley and Chelmondiston | Segregated or off road cycle path alongside B1456 | Transport Strategy | 2400000 | 0% | Talks- potential partners |  | 3.25 | 2 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 3 | 27 | Long
Cycling | Shotley Routes, Section 1 | Between Shotley and Shotley Gate | Segregated or off road cycle path alongside B1456 | Transport Strategy | 1200000 | 0% | Talks- potential partners |  | 3.25 | 2 | 3 | 2 | 3 | 2 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 3 | 27 | Long
Cycling | Shotley North Route, Section 3 | Between Chelmondiston Woolverson | Segregated or off road cycle path alongside B1457 | Transport Strategy | 1800000 | 0% | Talks- potential partners |  | 2 | 2 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 3 | 27 | Long
Cycling | Shotley, North to South, Eastern Connection | Between Chelmondiston and Holbrook | Segregated or off road cycle path alongside New Lane | Transport Strategy | 2400000 | 0% | Talks- potential partners |  | 3.5 | 2 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 3 | 27 | Long
Cycling | Shotley South Route, Section 3 | Between Stutton and Brantham | Segregated or off road cycle path alongside B1080/section of A137 | Transport Strategy | 2400000 |  | Talks- potential partners |  | 2.5 | 2 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 3 | 27 | Long
Walking & Cycling | Assington | The Street | Desire for a safe and/or segragated active travel route into village centre | Transport Strategy | £840,000 (From The Street/Hill Farm to The Street/Rose Green) £300,000 (From The Street/Hill Farm to A134) |  | Community con. |  | No data | 3 | 1 | 2 | 3 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 3 | 3 | 26 | Long
Walking & Cycling | Kersey to Hadleigh | Mill Lane/Stone Street | No walking or cycling provision to local services | Transport Strategy | £1,560,000 (if following road route - off road options should be explored) | 0% | Community con. |  | 4 | 3 | 2 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 25 | Long
Walking | Alpheton | A134 | Desire for a footway/path/pavement on route into or out of village to other neighbouring villages | Rights of Way and/or Transport Strategy | £2,580,000 (From A143/Old Bury Road to A143/A1092 in Long Melford) |  | Community con. |  | No data | 2 | 2 | 3 | 2 | 1 | 2 | 1 | 1 | 2 | 2 | 3 | 3 | 1 | 25 | Long
Walking & Cycling | Wherstead | Area off/across A137, The St | Desire for more accessbile walkways and pavements, segregated space for active travel and better crossings of roundabouts for pedestrians and cyclsits to Co-op site (large employer) | Transport Strategy | 420000 | 2% | LCWIP feedback |  | 3.3 | 2 | 1 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 24 | Long
Walking an cycling | Ipswich / Hintlesham | A1071 - stretch from the A1214 to Hadleigh Road. | No provision for pedestrians or cyclists to go from Pinebrook area to Hadleigh Road | Transport Strategy | 480000 |  | Community con. |  | 2.67 | 2 | 2 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 24 | Long
Walking | Aldham | The Street | Walking provisions | Rights of Way and/or Transport Strategy | £1,020,000 (from Bus Stop to Church) |  | Community con. |  | No data | 2 | 1 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 3 | 1 | 22 | Long
Walking | Sproughton / Burstall | Burstall Lane | Desire for pedestrain access/path between villages | Transport Strategy | £1,320,000 if its highways footway, cheaper option could be vergeside RoW |  | Community con. |  | No data | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 22 | Long
Walking | Sproughton / Washbrook | B1113 | Desire for pedestrain and cycle access/path between villages | Transport Strategy | £780,000 if its highways footway/cycleway |  | Community con. |  | 1.58 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3 | 1 | 22 | Long
Cycling | Glemsford | Park Lane | Desire for cycle route to Long Melford | Transport Strategy | £1,080,000 (based on village to A1092) - off road options maybe more viable |  | Community con. |  | 8 | 3 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 3 | 2 | 1 | 22 | Long
Cycling | Sudbury | Industrial area off A134, Northern Road | Cycle path provision | Transport Strategy | £600,000 estimate based on Addison Rd / Byford Rd distances |  | Community con. |  | 1.62 (Northern Rd not estate) | 1 | 1 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 22 | Long
Walking & Cycling | Nayland | Harpers Hill (A143) | No walking or cycling provision, this stretch particularly dangerous for cyclists | Transport Strategy | 390000 |  | Community con. |  | No data | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 2 | 2 | 22 | Long
Walking & Cycling | East Bergholt | Straight Road | School access route with no pavement, footpath or cycle lane | Transport Strategy | 900000 |  | Community con. |  | 2.29 | 2 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 3 | 2 | 2 | 22 | Long
Walking & Cycling | East Bergholt to Cattawade | Route along the B1070 | Desire for footpaths to be better connected or better crossings/off road provision to avoid having to walk/cycle on main road | Rights of Way and/or Transport Strategy | £2,520,000 (based on roadside highways infrastructure - off road options could be cheaper) |  | Community con. |  | 1.33 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 2 | 2 | 21 | Long
Walking & Cycling | Hadleigh to Whatfield | Whatfield Road | Desire for deidcated foot/cycle path from Whatfield to Hadleigh | Transport Strategy | 2160000 |  | Community con. |  | 1.81 | 1 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 21 | Long
Walking & Cycling | Boxford | The A1071 between Sand Hill and Calais Street | Desire for a footpath/cycle lane beside the Hadleigh bound carriageway. also suggestion that a connecting route onto the A1071 (currently closed off to cyclists) could reduce length that cyclists need to be on the A1071 - could cut some of main road out and reduce overall amount of investment needed? | Transport Strategy | £270,000 for carriageway |  | Community con. |  | 2.33 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 3 | 2 | 2 | 21 | Long
Walking | Raydon | Off road footpaths | Desire to link Raydon Wood with footpath to Hadleigh, and extend route following old railway line. | Rights of Way | £225,000 (based on path from existing to Railway walk & legal fees - may be a more depending on creating a joining?) |  | Community con. |  | No data (off road) | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 3 | 3 | 2 | 20 | Long
Cycling | Hintlesham / Flowton | Between Hintlesham and Hadleigh, Back Lane near Priory Road - Road that goes down from A1071 to Flowton | Desire for cycle path/cycle segragation on bendy stretch of road | Transport Strategy | £960,000 assuming only the A1071 stretch from Duke St to Priory Road |  | Community con. |  | 2.2 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 18 | Long
Walking & Cycling | Little Waldingfield | The Street (B1115) | Currently no pavement or provision for active travel down to the main road to connect with neighbouring villages | Transport Strategy | £1,200,000 (based on stretches not currently covered by any pavement - not including wideningof exsiting) |  | Community con. |  | No data | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 1 | 16 | Long
Note on I4: Katherine Davies: Price list: New cycleway/footway = £600 per metre Dropped kerb = £3,000 each New signage = £500 per sign New zebra crossing = £65,000 New traffic signals = £200,000 Pedestrian/Cycle crossing single carriageway road = £180,500 Pedestrian/Cycle crossing dual carriageway road = £250,000 Designating a Quiet Lane = £4,500 Rights of way stuff: unsealed surface – like crushed and rolled stone – is £35/m2. sealed surface, e.g. tarmac, is £80/m2. For any project that includes legal work (so changing the status from footpath to bridleway or diverting a route), the standard fee is £5,000. If buying land the minimum Environment Agency costs (£1,000), Planning Permission (£350) and Ecology Advice (£250). new fencing =£10/m new gates = £500 new footbridge £1000, new bridleway bridge = £3,000.
Note on M4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: using Geography: Middle Super Output Area, Cycling Flows: Route Network LSOA clickable and scenario: government target equality
Note on N4: Katherine Davies: 1 = if PCT is 0-2 2 = if PCT is 2 - 4 3 = if PCT is 4+
Note on V15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Potentially a 1, some areas there is limited space to add a path with adequate width.
Note on I19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: May be cheaper as some provision is already in place from the new housing development but difficult to tell as google maps is out of date. Off road alternatives may also be cheaper if viable.
Note on Q21: Katherine Davies: section 12.10 and objective 20
Note on Q22: Katherine Davies: section 12.10 and objective 20
Note on M23: Katherine Davies: note this is highest PCT score!
Note on W23: Katherine Davies: General Stour Valley connectivity
Note on Q26: Katherine Davies: section 6.3.2 relates to walking and cycling, but only in the context of new development
Note on S26: Katherine Davies: school access
Note on Q27: Katherine Davies: section 6.3.2 relates to walking and cycling, but only in the context of new development
Note on W27: Katherine Davies: Stour Valley visitor economy promoted routes
Note on N30: Katherine Davies: more people ay walk into Hadleigh but it is noted they may still use car to get to the Woods in the first place
Note on I31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Confused by their reference to Back Lane
Note on P32: Katherine Davies: there is some pavement already, and road is not significntly hazerdous for on road cycling